## Sheet1
PINKHAM WAY | [6 empty] | ISSUE 01
STRATEGIC RISK ASSESSMENT | [6 empty] | 27th March 2015
Objective: |  | To identify the probable, relative, high-level Planning Risks, Physical Risks and Cost Risks attached to any development of the site
Context / Basis of Reference: |  | This Risk Assessment has been prepared following proposals put forward by the NLWA for an MBT Waste Treatment Plant and
the London Borough of Barnet for a Waste Lorry Depot.
Pinkham Way Alliance has carefully studied the implications of these proposals. PWA and the London Borough of Haringey have
had discussions for the purpose of exploring the possibility of alternative uses for the site and its environs.
PWA has carefully considered these studies, and has concluded that development of the site would have significant negative
impact.
This Risk Assessment calibrates the risk stemming from the above studies and discussions, and it incorporates material prepared
for, and by the NLWA, LBH, LBB and PWA which is referenced in this matrix.
|  |  | RISK LEVEL | RISK LEVEL | RISK LEVEL
Item No | Subject |  | High | Medium | Low | Key References/Comments
1 | Impact on SINC Grade 1 Nature Conservation Value |  |  |  |  | ref: NPPF Core Principles 7 & 8 and paras 111 & 118,
Brownfield Sites of High Environmental Value
GLA Biodiversity Strategy and LBH Biodiversity Plan
Special Criteria apply to land as part of an Ecological
Green Corridor Network linked to Metropolitan Land
2 | Ecological Impact |  |  |  |  | ref: Preliminary Ecological Appraisal prepared by Huma
Pearce & Denis Vickers for PWA, date October 2013;
Reference No: 2013_012
Preliminary Invertebrate Survey 2014-2015 by
Edward Milner identifies rich "Open Mosaic" Area
ref: LUC Report, Oct 2014 for LBH, Appendix 7
3 | Environmental Corridor & Metropolitan Open Land |  |  |  |  | ref: NPPF para 109,113 and 117; coherent ecological
networks and wildlife corridors
ref: Mayor's Biodiversity Strategy, Appendix 1, items,
A1.2.17; A1.2.18 and A1.2.19:- sites of importance are
included in (green) corridors, but these deserve protection
in their own right
MOL land abuts site and forms part of site containing
features of nature conservation and habitat interest and
forms part of an ecological corridor
All London Green Grid (ALGG): Mayor's Policy to promote
the design and delivery of green infrastructure across
London
4 | Existing Culvert |  |  |  |  | ref: Jacobs Development Constraints Report, April 2008 -
para 2.4 and 2.9 - condition of culvert unknown and its
vulnerability to contamination; risks associated with
flooding
ref: Arup Scoping Report, 07/03/11, para 3.8
ref: Environment Agency letter to LBH, date 20/03/14
Deculverting watercourses are to include a set back to
incorporate at least an 8m buffer zone.
Buffer Zones are to provide habitat and 'green corridors'
for flora and fauna; support the ecology and natural
functioning of the watercourse and provide safe access
alongside the watercourse
ref: LBH Biodiversity Action Plan and London Rivers Action
Plan
5 | Loss of Existing Environmental Benefit |  |  |  |  | ref: Environmental Protection Act, 1990
ref: Air Quality Strategy for London, 2010
London Borough of Haringey, Air Quality Action Plan 2010-
2018, Feb 2011
ref: Arup Scoping Report, 07/03/11, para 3.1 - It is
recognised that the site is sensitive in terms of Air Quality
The site is located within LBH's Air Quality Management
Area and in close proximity to the AQMAs of Barnet and
Enfield
Health Impact Assessment would be required
6 | Planning Risk |  |  |  |  | Incompatibility with Adopted Planning Framework - NPPF,
London Plan and London Borough of Haringey and DEFRA
Guidance
Potential for call-in by the Mayor or Secretary of State for
determination prior to decision by the Local Authority
7 | Contaminated Land |  |  |  |  | ref: Jacobs Development Constraints Report, April 2008 -
para 2.2, Lead at concentrations above CLEA Guidelines
para 2.3, Microbiological Risk
para 2.4, Groundwater Contamination
para 2.5, Gas Protection Measures
Extent of Contaminated Land is approx 80% of site area
ref: Arup Scoping Report, 07/03/11, para 3.2 - confirm the
following:- Elevated concentrations of lead; Elevated
concentrations of microbial contaminants in soils and
groundwater; Further gas monitoring required
8 | Historic Landfill |  |  |  |  | ref: Jacobs Development Constraints Report, April 2008,
para 2.7 - The volume of buried concrete waste is difficult
to quantify. Extensive waste has been deposited through-
out the site
9 | Geotechnical Ground Conditions |  |  |  |  | ref: Jacobs Development Constraints Report, April 2008,
para 2.8 Settlement & Foundation Design - The loose and
variable nature of the Made Ground poses a risk of
excessive settlement for foundations located within it.
This risk is compounded by potential infiltration of water
which can lead to localised ground collapse in poorly
consolidated areas.
A thin covering of Made Ground provides a pathway to
weathered London Clay, the surface properties of which
sensitive to variations in moisture content.
10 | Existing Roads Infrastructure |  |  |  |  | ref: Arup WIDP 27/10/2009: High Risk
Residential Roads to west of site unable to accommodate
any increase in traffic movements
11 | Access to and Egress from Site |  |  |  |  | ref: Arup WIDP 27/10/2009: High Risk
ref: Arup Scoping Report, 07/03/11, para 3.6
Access from Orion Way not possible without destroying
land rich in invertebrates
Direct access / egress to and from the North Circular Road
(A406) is not feasible
12 | Public Transport Links |  |  |  |  | ref: PTLA rated 1a (LBH lowest rating)
The site is isolated and there is a lack of transport
accessibility
ref: Atkins ELS, Feb 2015, para 5.41 - site contaminated
and not close to public transport
13 | Flood Risk |  |  |  |  | ref: Ove Arup & Partners Ltd, WIDP, RevB, 27/10/09
Figure 2. Pinkham Way Flood Risk
ref: Environment Agency letter to LBH, date 20/03/14
Strategic Flood Risk Assessment required
Environment Agency require a thorough evidence base in
the form of a sequential test supported by SFRAs
Sites with potentially contaminated land will be expected
to submit a preliminary risk assessment in line with para
007 of the National Planning Practice Guide. Any sites with
former contaminative uses would be subject to land
quality conditions
14 | Conflict of Ownership |  |  |  |  | Landlocked part of site is owned by LB Barnet therefore
Access would be required across MOL or "Open Mosaic"
LBB area equates to approx 40% of total PW site area
15 | Tree Preservation Orders |  |  |  |  | Protected by legislation
Town & Country Planning Act 1990
Town & Country Planning (Trees) Regulations 1999
16 | Existing Topography |  |  |  |  | ref: Jacobs Development Constraints Report, April 2008,
Figure 4, Topographical Survey
Figure 6, Areas of Significant Gradient
ref: Arup Scoping Report, 07/03/11, para 3.4.1 - the
topography of the site is very uneven due to former
landfill and sewage works; the level difference is approx
15metres between the highest southernmost point of the
site and the lowest level adjacent to Pinkham Way/NCR
17 | Utilities Infrastructure |  |  |  |  | ref: Jacobs Development Constraints Report, April 2008,
para 4.3 and para 4.4 and Figure 3
EDF Electricity buried cables in an East-West central location
across the site
18 | Network Rail |  |  |  |  | British Transport Commission Act 1949
NR Guidelines to be followed in conjunction with building
works in proximity to NR Property - ie structural stabilty
of NR property, drainage and flood risk implications,
foundations, electromagnetic interference, fire risk, etc
19 | Cost Risk (VFM) |  |  |  |  | This Strategic Assessment indicates that there is a
significantly high level of cost risk attached to development
of this site.
Additionally, it must be noted that there is considerable
potential for heightened Cost Risks attached due to the
cumulative impact arising from the synergy of elements
that comprise this Site of Importance for Nature
Conservation (SINC) - Borough Grade 1 Importance.
Consequently, the site is not likely to provide VFM for any
developer, let alone a public body.
20 | Transfer of Long-Term Legal Risk |  |  |  |  | Ref: The Environmental Protection Act 1990 and the
Contaminated Land (England) Regulations 2000
Case (Transco) - long term (in perpetuity) Liability on
cleaning up contaminated land - R (on the application of
National Grid Gas plc (formerly Transco plc) (Appellants) v.
Environment Agency (Respondents) (Civil Appeal from Her
Majesty's High Court of Justice) [2007] UKHL 30
Other references considered in the preparation of this document include (but are not limited to) the following:-
National Planning Policy Framework, 2012
The London Plan, March 2015
DEFRA; Local Sites: Guidance on their Identification, Selection and Management, 2006
The Conservation of Habitats and Species Regulations, 2010
GLA/London Wildlife Sites Board: SINC Selection Process - Update, March 2013
The Habitats Directive 1992/43/EEC
Environmental Protection Act, 1990
The Air Quality Strategy for England, Scotland, Wales and Northern Ireland 2007
Air Quality Strategy for London, 2010
London Borough of Haringey Air Quality Action Plan 2010-2018, Feb 2011
NSCA - National Society for Clean Air
Planning Policy Statement 23, Planning and Pollution Control
EU Directive, 2004/35/EC Environmental Liability
EU Water Framework Directive, 2000/60/EC
DEFRA: Guidance for Public Authorities on Implementing the Biodiversity Duty, May 2007
DEFRA: Guidance on the Legal Definition of Contaminated Land, July 2008
Knox G. Atmospheric pollutants and mortalities in English local authority areas; Journal of Epidemiology and Community Health 2008;62:442-447
Maas J et al. Green space, urbanity and health: how strong is the relation? Journal of Epidemiology and Community Health 2006;60:587-592
PPS10 Planning for Sustainable Waste Management 2005
Update to PPS10: 30 March 2011
PPS10 Companion Guide 2006
NOTES:
This outline strategic risk assessment is subject to further development as more detailed information becomes available
Prepared by: Paul Scott BSc(Hons) Dipl Arch Cert APDM ARB RIBA - Chartered Architect & Project Manager